# North Somerset Male Health Action Plan 2025-2029

Vision - Set a national standard for male mental health, emotional fitness, and wellbeing in North Somerset.​

Mission - Create collaborative spaces of welcoming, encouragement and support that promotes learning and healthy lifestyles for males​

| By 2029 we want to (objective) | What we will do (action) | Our target | By when (timeline) | Delivery lead |
| --- | --- | --- | --- | --- |
| Establish a male health programme of work across North Somerset | Organise and chair the North Somerset Male Health Steering group. | Meet 4 times a year and manage the development and monitoring of the action plan | Finalise and publish action plan September 2025 | North Somerset Council Mental Wellbeing Team (NSC) |
|  | Produce an annual data summary of the mental health needs of men and boys in North Somerset. | Publish an easy to read and understand data summary | Annually First to be published October 2025 | North Somerset Council Business Intelligence Team |
|  | Produce a male mental health needs and assets assessment | Publish a review of mental health needs and assets in North Somerset to guide future priority areas | December 2025 | North Somerset Mental Wellbeing Team (NSC) |
|  | Generate funding to support implementation of the action plan and interventions. | To secure at least £10k a year | Annually by end March each year. | North Somerset Male Health Action Circle |
| Build capacity for those who work with men and boys to adopt a gendered competent and male friendly approach. | Review the options of developing a training programme to cover the areas of male mental health. | Decide on whether developing a training programme is a good use of limited funds. | March 2026 | North Somerset Male Health Action Circle |
|  | Run and develop the North Somerset Male Health Group encouraging new members ​ | To meet 4 times a year and invite speakers to talk about other key areas of work in North Somerset. Trial a working lunch option with networking | Ongoing First to happen in September 2025 | North Somerset Male Health Action Circle North Somerset Male Health Action Circle |
| Support the delivery of health promotion campaigns and projects targeted at improving male health. | Help to organise the annual Weston Hornets awareness raising event | Increase the number of attendances, measured through feedback numbers. | Annually | Steve Barnard, Male Health action circle member |
|  | Attend 3 key events a year across North Somerset | Develop an events calendar to highlight where we will attend and who will take the lead. Develop a short survey that can be used to capture feedback about what people see as the main health issues for men living in North Somerset to be used at events | September 2025 September 2025 | North Somerset Male Health Action Circle Male Heath Action Circle |
|  | Develop promotional materials with the New North Somerset Male Health logo | Design a banner and posters to be used at events. | August 2025 | North Somerset Council Mental Wellbeing Team (NSC) and With You. |
|  | Update Male health area on the Better health Website to include a summary of the groups involved and signpost people to further help | Increase the number of hits to the page by 50%. | December 2025 | North Somerset Council Mental Wellbeing Team (NSC) |